## Risk Register
Year |  |  |  | Risk Impact |  |  | Risk Likelihood |  |  | Risk Response
Lead Division |  |  |  | 1 | Very Minor |  | 1 | 1 - 20% |  | Avoid
Date Updated |  |  |  | 2 | Minor |  | 2 | 21 - 40% |  | Reduce
|  |  |  | 3 | Moderate |  | 3 | 41 - 60% |  | Fallback
|  |  |  | 4 | Significant |  | 4 | 61 - 80% |  | Transfer
|  |  |  | 5 | Catastrophic |  | 5 | 81 - 99% |  | Share
Accept
[6 empty] | Pre Mitigation Scores |  |  | Current Scores |  |  | Post Mitigation Scores
Risk ID | Program | Risk Name | Risk Description | Date Captured | Risk Owner | Pre-Mitigation Impact | Pre-Mitigation Likelihood | Pre-Mitigation Score | Current Impact | Current Likelihood | Current Score | Post-Mitigation Impact | Post-Mitigation Likelihood | Post-Mitigation Score | Risk Response | Mitigation Plan / Actions | Current Status | Risk Proximity | Workstream | Operational or Project Risk | Escalation Level | Last Review Date | Next Review Date | Target Completion Date | Historical Progress | Notes
IARSK0001 | Automate the internal audit activities through the acquisition and implementation of an audit software system | Systems Acquisition and Implementation Risk | The automation process may fail to capture all necessary technical specifications, potentially leading to incomplete or inaccurate audit coverage | 2026-07-22 | Director IA |  |  |  | 2 | 3 | 6 |  |  |  | Accept | Adopt a structured project governance approach | In progress | medium term | Procurement | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | There might be a delay in acquisition, execution and implementation of the audit software due to budget constraints. | 2026-07-22 | Director IA |  |  |  | 2 | 3 | 6 |  |  |  | Accept | Adopt a structured project governance approach | In progress | medium term | Procurement | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Loose security settings during deployment that exposes sensitive financial or personal data | 2026-07-22 | Director IA |  |  |  | 2 | 3 | 6 |  |  |  | Accept | Adopt a structured project governance approach | In progress | medium term | Procurement | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Staff rejection or under-utilisation of the system due to lack of intuitive training or capacity building | 2026-07-22 | Director IA |  |  |  | 2 | 3 | 6 |  |  |  | Accept | Adopt a structured project governance approach | In progress | medium term | Procurement | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | The implementation of the audit management software system may not be completed or could be abandoned, jeopardizing the objective of automating internal audit activities | 2026-07-22 | Director IA |  |  |  | 2 | 3 | 6 |  |  |  | Accept | Adopt a structured project governance approach | In progress | medium term | Procurement | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
IARSK0002 | Build capacity of Internal Audit staff in operational areas such as Procurement, Legal and Regulatory Management | Human Capital/ Competency Risk | The training may not achieve its intended purpose when existing legal frameworks become outdated and there's no further training for existing staff | 2026-07-22 | Director IA |  |  |  | 3 | 3 | 9 |  |  |  | Accept | Targated Capacity Building | In progress | Short term | Trainings | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Trained staff may resign to seek better opportunities, potentially leading to a loss of expertise and disruption in key operational areas | 2026-07-22 | Director IA |  |  |  | 3 | 3 | 9 |  |  |  | Accept | Succession and Retention strategy | In progress | Short term | Trainings | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Financial constraints may limit the ability to implement the planned training for Internal Audit staff. | 2026-07-22 | Director IA |  |  |  | 3 | 3 | 9 |  |  |  | Accept | Dedicated Annual Training Budget | In progress | Short term | Trainings | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
IARSK0003 | Build the capacity of Internal Audit staff on Continuous Professional Learning | Human Capital/ Competency Risk | Scheduled capacity-building programs may not be conducted as planned, which could impede the objective of enhancing the Internal Audit staff's knowledge and skills on Professional Frameworks and Standards. | 2026-07-22 | Director IA |  |  |  | 3 | 4 | 12 |  |  |  |  | Targated Capacity Building | In progress | Short term | Trainings | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | The Authority may not approve the budget for capacity building initiatives aimed at developing the Internal Audit staff's knowledge of International Public Sector Accounting Standards (IPSAS) and Global Internal Audit Standards. | 2026-07-22 | Director IA |  |  |  | 3 | 4 | 12 |  |  |  | Accept | Dedicated Annual Training Budget | In progress | Short term | Trainings | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
IARSK0004 | Develop an Annual Risk-based internal audit work plan | Strategic Planning Risk | Emerging Risks are not identified and captured into the annual audit work plan. | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Structured Methodology, Stakeholder Engagement and Continuous Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Lack of adequate capacity building for Internal Audit staff on External Source (Government, Sector Ministry, IAA, etc) Directives for the inclusion of specified thrust areas into the Annual Workplan. | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Structured Methodology, Stakeholder Engagement and Continuous Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
IARSK0005 | Conduct audit of the activities and systems at the NCA in the thrust areas approved in an annual Internal Audit Plan and any other thrust areas required in a year | Audit Execution Risk | The audit may not be completed on a timely basis due to the non-availability of auditees, potentially impacting the development of a risk-based internal audit work plan. | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Resource bottlenecks due to compressed timelines; sudden staff turn-over; overlapping engagement schedules | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Budgetary constraints may hinder the execution of the annual Internal Audit Plan and limit the ability to conduct audits in additional thrust areas that may be requested in the year | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Poorly defined initial parameters and discovery of unexpexted control deficiencies. | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Data disruptions due to auditee teams being slow to provide evidence | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Data disruptions due to extraction errors in legacy IT systems | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Auditing reporting delays due to Management responses | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Audit fatigue due to multiple overlapping regulatory, Internal and External requests on Internal Audit Division | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress
|  |  | Obsolescence due to rigid adherence to outdated audit work plan and failure to update when new macro risks emerged | 2026-07-22 | Director IA |  |  |  | 2 | 4 | 8 |  |  |  | Accept | Standardized Methodology, Quality Controls, and Performance Monitoring | In progress | Short term | Stakeholder Engagements | Operational | DG | 22/7/2026 | 30/9/2026 | 31/12/2026 | Stakeholder Engagement | Work in progress

## Lookups
Risk Impact |  |  | Risk Likelihood |  |  |  | Risk Response
1 | Very Minor |  | 1 | 1 - 20% |  |  | Avoid
2 | Minor |  | 2 | 21 - 40% |  |  | Reduce
3 | Moderate |  | 3 | 41 - 60% |  |  | Fallback
4 | Significant |  | 4 | 61 - 80% |  |  | Transfer
5 | Catastrophic |  | 5 | 81 - 99% |  |  | Share
Accept
| Impact | 5 | 10 | 15 | 20 | 25
|  | 4 | 8 | 12 | 16 | 20
|  | 3 | 6 | 9 | 12 | 15
|  | 2 | 4 | 6 | 8 | 10
|  | 1 | 2 | 3 | 4 | 5
Likelihood