## Info Tech
| Objective/Process | Risk Category | Risk Description | Risk Source | Risk Event | Risk Cause | Risk Owner | Risk Action Owner/Lead Officer | Risk Likelihood | Risk Impact | Inherent Risk Rating | Risk Response (Control) | Residual Risk
1 | Conduct Industry research on trends and emerging technologies |  | Not producing any research paper |  |  | Delays in data collection | Director RIPS | Unit Head, Research and Innovation | 3 = Possible | 3= Moderate | 9=Moderate | Improve timely data collection | Lack of credible data on trends in the industry. Lack of data to aid decision making on emerging technologies.
2 | Conduct Regulatory Impact Analysis |  | Is the project, the appropirate solution to the identified problem? Recommendations from the analysis is not considered |  |  | Regulatory impact analysis is not priortised in undertaking projects | Director RIPS | Unit Head, Research and Innovation | 5= Certain | 4= Major | 20 = Critical | Be intentional to priortise Regulatory Impact Analysis
3 | Implementation of the Authority's Strategic Plan and yearly corporate objectives |  | Delay in achievement or non-achievemnt of set objectives due to financial constraints and/or procurement delays. |  |  | 1. Poor revenue inflows 2. Exchange rate fluctuations 3. Delay in procurement process( late request, late approvals etc) | Director RIPS | Director Finance Head of Procurement | 4= Likely | 4= Major | 16 | 1. Improve revenue collection to help generate funds to meet the budgetary requirements for the objective. 2. Alternative sources of revenue 3. Implement procurement automation tools to ensure the timely processing of purchase orders.
4 | Monitor and evaluate the performance of the Corporate Strategic Objectives |  | Delay in completion of performance report for Management, Board and MoCD as a result of late submission of Divisional performance data to the RIPS Division |  |  | Failure by Divisions to prioritise their role in the performance monitoring. | Director RIPS | Divisional Heads | 3=Possible | 3=Moderate | 9 | 1.Escalate late submission of Divisional performance data for the Director General's intervention. 2. Automate the submission of performance data to ensure effectiveness and efficiency
5 | Industry Data Collection and Management |  | 1. Inability to meet timelines in the publication of Quarterly Statistical Bulletin. 2. Inability to meet annual data collection targets. 3. Inability to provide certain data request from external stakeholders. |  |  | 1. Delay in submission of data from the Service Providers, which also delays the meeting of the Tripartite meetings to review submitted data.Delay in the sign-off for publication on the NCA website. 2. Non-submission of data from some Service Providers 3. The Authority do not collect data on all the services that we regulate | 1. Director, RIPS 2. Director, RIPS 3. Director, RIPS | 1. Chief Manager,Data and Analytics Unit 2. Chief Manager,Data and Analytics Unit 3.Chief Manager,Data and Analytics Unit | 4 5 5 | 4 4 4 | 16 20 20 | 1. Adherance to timelines by the Service Providers in submitting data. Tripartite adhering to laid down procedures and timelines in executing its mandate. 2. Service Providers should receive the penalties associated with non-submission of Data. 3. Data collections should include all Licensed service provider under the Authority.
6 | Implement guidelines for the computation of 1% Regulatory Fees |  | 1. Delay in Gazetting Guidelines for the computation of 1% Regulatory Fees for industry use. 2. Non-compliance to guidelines for computation of 1% regulatory fee by MNOs |  |  | 1. Guideline cannot be enforced if document is not gazetted. 2. Revenue assurance for the Authority will be impeded | Director Legal, Director RIPS | Chief Manager- Market Regulations, Senior Manager- Legal | 2 2 | 4 | 8 | 1. Organise Quarterly workshops to resensitize Operators on compliance and evaluate new challenges. 2. Prefer penalties for non-compliance of guideline application. 3. Collect Feedback for continous improvement 4. Annually review the guidelines on lessons learnt.
7 | Determine and implement Wholesale Interconnect Rate (WIR) for 2024- 2026 |  | Delay in determining the Wholesale Interconnect Rate (not meeting the timeline) |  |  | 1. Delays in providing industry information for the work of consultant. 2. Changes in Market dynamics | DG, Director RIPS, Director RA | Chief Manager- Market Regulations, Manager | 1 | 1 | 1 | 1. Organise Workshops for continous sensitization. 2. Perfer percuniary penalties for non-compliance. 3. Great channels for escalation on dispute resolution on the application of the WIR.