## Sheet1
2026 CORPORATE WORKPLAN
NO. | STRATEGIC PILLAR | PROGRAMMES | GOAL(S) | KPI | TARGET | BASELINE | KEY ACTION POINT | BUDGET (GHC) | WEIGHT (100%) | TIME SCHEDULE
[10 empty] | START | END
1 | Research, Innovation and Process Improvement | Produce and Publish Industry/Statistical reports | To highlight trends and developments in the telecommunications and broadcasting industry for stakeholder information | 1. Number of Statistical bulletins editions published 2. Number of CIR editions published | 1. 4 (1 Per quarter) 2. 1 | Seven (7) CIR and Thirty-two (32) Statistcal Bulletin | 1. Produce the Q4 2025 Statistical Bulletin | 110000 | 15 | January | March
[7 empty] | 2. Produce the Q1 2026 Statistical Bulletin. |  | 15 | April | June
[7 empty] | 3. Produce the Q2 2026 Statistical Bulletin |  | 15 | July | September
[7 empty] | 4. Produce the Q3 Statistical Bulletin |  | 15 | October | December
[7 empty] | 4. Produce the 2025 Communication Industry Report |  | 40 | January | June
2 | Research, Innovation and Process Improvement | Coordinate activities of Research Units in all Divisions | To have mainstream research in the Authority to enhance knowledge and drive evidence based decisions | Number of Divisional research collaborations done | 3 divisional research collaborations completed | 0 | 1. Establish a Research Coordination Committee comprising representatives from relevant Divisions. 2. Develop and implement an annual divisional research agenda aligned with organizational priorities. 3. Organize quarterly research planning and review meetings. 4. Create a central repository/database for all research activities and outputs. 5. Facilitate at least one cross-divisional collaborative research project per quarter. 6. Produce and disseminate periodic reports on divisional research activities and outcomes. |  | 15 | January | December
3 | Research, Innovation and Process Improvement | Conduct industry research on trends and emerging technologies. | To keep abreast with trends and emerging technologies to inform regulatory practices and policies | Number of desktop researches conducted | 3 | Three (3) industry research | 1. Identify priority emerging technologies and industry trends for assessment. 2. Conduct desktop research on Artificial Intelligence (AI) and its impact on telecommunications regulation. 3. Conduct research on 5G/6G developments and deployment best practices. 4. Conduct research on emerging digital infrastructure technologies such as cloud computing, IoT and Open RAN. 5. Engage stakeholders and industry experts to validate findings. 6. Prepare and present policy briefs and recommendations based on research findings. |  |  | April | December
4 | Research, Innovation and Process Improvement | Online portal for the collection of data from authorised service providers | To develop, deploy, and continuously improve an online data collection platform for telecom operators and licensees submitting regulatory data to the NCA. | Percentage completion | 70% | Electronic forms developed for online data collection | 1. Develop Product Requirement Document |  |  | January | March
[7 empty] | 2. Develop user interface of the portal |  |  | April | June
[7 empty] | 3. Develop backend interface of the portal |  |  | April | June
[7 empty] | 4. System Testing and acceptance |  |  | July | September
[7 empty] | 5. Mounting the final product on servers and the appropriate platform |  |  | July | September
[7 empty] | 6. Orientation and Training of Staff and External Users |  |  | October | December
5 | Research, Innovation and Process Improvement | Monitor and report on the performance of the Corporate Strategic Objectives | To drive the achievement of the Authority's Strategic goals | Number of performance reports produced | 4 | Annual performance reports from 2017 to date | Work with Divisions to develop and review the 2026 corporate work plan |  | 25 | January | March
[7 empty] | Review and analyse objectives received from all Divisions to track performance of Q1 2026 |  | 12.5 | January | March
[7 empty] | Review and analyse objectives received from all Divisions to track performance of Q2 2026 |  | 12.5 | April | June
[7 empty] | Review and analyse objectives received from all Divisions to track performance of Q3 2026 |  | 12.5 | July | September
[7 empty] | Review and analyse objectives received from all Divisions to track performance of Q4 2026 |  | 12.5 | October | December
[7 empty] | Produce Performance report and submit to Management after quarter one |  | 8.4 | April | April
[7 empty] | Produce Performance report and submit to Management after quarter two |  | 8.3 | July | July
[7 empty] | Produce Performance report and submit to Management after quarter three |  | 8.3 | October | October
6 | Research, Innovation and Process Improvement | Develop structures and fora to review internal policies and processes | To establish structured and collaborative mechanisms for the periodic review and improvement of internal policies and processes and ensuring they remain effective. | Number of SOP sensitization workshops carried out | 16 | Divisional SOPs drafted and reviewed | 1. Establish Process Review Framework Develop process assessment methodology, templates and review criteria Approved Process Review Framework 10% - Q1 2. Identify Critical Business Processes Map key operational processes across divisions Process inventory developed 15% Q1 3. Conduct Process Mapping and Documentation Document current workflows, roles, approvals and timelines Current-state process maps 15% -Q2 4. Conduct Process Gap and Efficiency Assessment Identify bottlenecks, duplication, delays and control weaknesses Process assessment report 15%-Q3 5. Develop Process Improvement Recommendations Design improved workflows and operational solutions Process improvement plan 15%-Q3 6. Validate Improved Processes Engage process owners and stakeholders for review Validated process redesign documents 10% -Q4 7. Implement Approved Process Improvements Introduce revised workflows, tools and procedures Implemented improved processes 10% -Q4 8. Monitor Process Performance Track efficiency gains, turnaround times and compliance Process performance report 10% -Q4 | 200000 |  | January | June
7 | Research, Innovation and Process Improvement | Organize innovation and strategic foresight engagements with staff | To develop a culture where innovation is actively encouraged, and strategic thinking is embedded in all levels of the organization | Number of online sessions | 4 | Divisional SOPs | 1. Engage staff on the processes involved in innovation and foresight activities. |  |  | June | December
[7 empty] | 2. Conduct four interactive online/in-person sessions to promote innovative thinking and strategic foresight. |  | April | December
[7 empty] | 3. Encourage staff to submit innovative ideas and research topics for organizational improvement. |  | April | Decenmber
[7 empty] | 4. Document insights and outcomes from each engagement session for continuous learning and improvement. |  | April | Decenmber
[7 empty] | 5. Share session outcomes with Divisional Head to inform strategic planning and decision-making. |  | April | Decenmber
8 | Research, Innovation and Process Improvement | Evaluate the financial performance of Service Providers | To assess the Financial health and efficiency in the telecoms industry | Number of reports on the financial health of service providers | 8 financial performance reports completed | A draft report on a 5 year financial analysis for MNOs covering 2019 to 2023 | Analyse extracted data from the audited Financial report of the following sevices MNOs, BWAs, Towers, ICH, Fiber, PayTV from 2021-2025 to ascertain their financial health for policy direction |  | 40 | April | June
[7 empty] | Analyse extracted data from the audited Financial report of the following sevices satellite, managed services, submarine, IWCL, Gateway from 2021-2025 to ascertain their financial health for policy direction |  | 30 | July | September
[7 empty] | Analyse the extracted data from the 2026 management account of the following sevices; MNOs, BWAs, Towers, ICH, Fiber, PayTV, satellite, managed services, submarine, IWCL, Gateway |  | 30 | October | December
[7 empty] | Develop key financial indicators including profitability, liquidity, solvency and efficiency ratios. Produce sector-specific financial health assessment reports and industry outlook reports. Present findings and recommendations to Management for policy and regulatory decision-making. Benchmark financial performance against regional and international industry trends. Maintain a financial performance database for periodic monitoring and reporting. |  |  | Quarterly | Quarterly
9 | Research, Innovation and Process Improvement | Implement "Tech and Innovation Insight" programme | To keep abreast with trends in technology and innovations in the telecommunications industry | Number of industry engagements | 3 | 0 | 1. Finalise Concept Notes with feedback from DRIPS. 2. Engage potential participants on the concept and their buy-in. 3. Develop a schedule for the events for the year. 4. Draft invitation letters to participants and exhibitors for DG Signature. 5. Collaborate with Corporate Affairs to organise the Events. |  |  | January | December
10 | Research, Innovation and Process Improvement | Benchmark study on Competition Regulations | To understudy best practices in competition regulation in telecommunications/ICT | Number of benchmark visits carried out | 3 | Three (3) benchmark visits | 1. Identify three regulatory authorities/institutions with recognized competition regulatory frameworks. 2. Develop benchmark study terms of reference and assessment criteria. 3. Conduct benchmark visits and stakeholder engagements with selected institutions. 4. Document best practices, lessons learned and regulatory innovations from benchmark studies. 5. Prepare comprehensive benchmark reports with recommendations for implementation. 6. Organize dissemination sessions with relevant divisions and management. 7. Develop an action plan for adopting suitable competition regulatory best practices within the Authority. | 1200000 |  | February | December
11 | Research, Innovation and Process Improvement | Benchmark study on Artificial Intelligence (AI) regulations in Africa | Gather data on AI regulation to ensure the Authority contributes meaningfully to the review and Implementation of National AI Strategy. | Percentage completion of the study on AI policies and regulations in Africa | 100% | National AI Policy and Strategy | 1. Identify Countries with existing frameworks on regulating AI 2. Conduct comparitive analysis on the selected countries' framework with the draft Naational AI Policy and Strategy of Ghana. 3. Produce report indication similarity and differences. 4. Make recommendations on best practices to adopt. |  |  | January | March
12 | Research, Innovation and Process Improvement | Coordinate and track implementation of initiatives to move Ghana from leading to Advanced under the ITU G5 Benchmark | To achieve a progressive improvement in Ghana's rank on the G5 Benchmark, from Advanced to leading through coordinated regulatory reforms. | 1. National G5 Benchmark roadmap developed 2. Progress reports produced 3. Benchmark score improvements achieved | 1. 1 roadmap 2. 4 reports (1 per quarter) 3. At least one generation improvement by year-end | Current G5 status (Advanced) | 1. Conduct a gap analysis between current G3 status and G5 requirements across all ITU pillars (Access, Usage, Quality, etc.) |  | 30% | March | December
[7 empty] | 2. Develop a comprehensive National G5 Roadmap with clear actions, responsibilities, and timelines. |  | 30% | March | December
[7 empty] | 3. Track and report on implementation progress quarterly. |  | 40% | March | December
13 | Research, Innovation and Process Improvement | Policy Advisory on Emerging Technologies and Regulatory Trends | Provide timely strategic advice to management on emerging technologies and their regulatory implications | Number of policy briefs, advisories and position papers produced | 4 advisories per year | Ad hoc policy assessments | Draft, review, and finalize policy briefs. |  | 100% | March | December