## Legal Div
No. | Objective/Process | Risk Category | Risk Description | Risk Source | Risk Event | Risk Cause | Existing Control | Risk Owner | Risk Action Owner/Lead Officer | Risk Likelihood | Risk Impact | Inherent Risk Rating | Residual Risk
1 | Retrieve Public Funds from International Wholesale Carrier Licence(IWCL) defaulters | Operational | Absence of tangible collateral to attach in execution of a favourable judgement could make it difficult to retrieve funds. | 1. Harsh Market conditions | Inadequate Debt Recovery Process leading to the IWCL's defaulting payment of invoices. | Incomplete documentation: Absence of provision in the licence requiring security or collateral against potential default at the contract stage. | Issuance of Demand Notices and commencement of court action | Director Regulatory | Officer in charge of invoicing | 4 | 4 | 16
2. Indebtedness of IWCL
2 | Review NCA Legislation to ensure that it responds to the changing business landscape | Operational | Harmonisation of domestic legislation with international legislation and conventions to address anticipated risks and to keep pace with emerging technologies | Legislations not in harmony with international legislations and conventions | Legislative framework that does not respond to the changing business landscape and emerging technologies | i. Inadequate funds | Reviews done on case by case basis with available resources | Directors HR & Finance | Deputy Directors Finance, & HR | 3 | 3 | 9
ii.The availability of required expertise to undertake the review of NCA Legislation.
3 | Draft licences and review legal documents to ensure compliance with provisions of various legal documents | Operational | Non compliance of the review of licences and legal documents with domestic and international legislation and conventions presents risks such as law suits. | i. Drafting of regulatory documents, licenses & Application guidelines without input from the Legal Division at inception. ii. Dearth of required technical and legal competencies | Licences and legal documents need to be drafted in compliance with the legislative provisions. | Documents not conforming with domestic and international standards | Reviews done on case by case basis with available resources | Directors HR & Finance | Deputy Directors Finance, & HR | 3 | 3 | 9
4 | Provide legal advice to all Divisions of the NCA and the Board to increase qaulity, responsivenss and efficiency of the Authority | Operational | Delays in the provision of legal advice | Delays in the provision of legal advice | Unclear timelines for submitting the legal advice | i. Delays in submission of request | On an "as is" basis. | Originators | Director Legal | 2 | 2 | 4
ii. Delays in responding to the request
5 | Monitor the passage of all laws to extract industry related issues to enhance the work of the Authority | Operational | Some laws affecting the communications industry may be passed without the knowledge of the Authority which may have dire consequence on the operations of the Authority. | Legislations passed may have a negative impact on the work of the Authority. | The Authority must monitor the passage of laws that may affect the communications industry. | Enormity of the task and the expertise required | Regular monitoring of parliamentary proceedings, Bills & Regulations presented to Parliament and review of draft Bills and Regulations initiated by agencies within the communications sector | Directors HR & Legal | Director Legal | 3 | 3 | 9
6 | Provide legal representation on issues arising from actual and anticipated law suits and provide support to external solicitors | Operational | Inability to represent the Authority in court due to several law suits leading to a breach of court rules | Case overload and contingent claims | Inability to represent the Authority in court due to several pending law suits. | Non-availability of in-house lawyers/external lawyers to represent the Authority in court. | Close collaboration with all Divisions on a proactive basis | Directors Regulatory & Legal | Deputy Directors Regulatory & Legal | 1 | 2 | 2
7 | Train and/or share knowledge with staff of the Authority including Regional Offices on the NCA Legal Framework | Operational | Lack of staff understanding of the relevant legislations within the communications industry leading to misinformation. | Inadequate training of staff on the legislations within the communications industry | Negative impact on the staff performance | Inadequate training of staff | Collaboration with HR and ROD for training content and timelines | Directors Finance & HR | Deputy Director, HR | 1 | 2 | 2