## Risk Register
Division |  |  |  | Risk Impact |  |  | Risk Likelihood |  |  | Risk Response
Lead |  |  |  | 1 | Very Minor |  | 1 | 1 - 20% |  | Avoid
Date Updated |  |  |  | 2 | Minor |  | 2 | 21 - 40% |  | Reduce
|  |  |  | 3 | Moderate |  | 3 | 41 - 60% |  | Fallback
|  |  |  | 4 | Significant |  | 4 | 61 - 80% |  | Transfer
|  |  |  | 5 | Catastrophic |  | 5 | 81 - 99% |  | Share
Accept
[6 empty] | Pre Mitigation Scores |  |  | Current Scores |  |  | Post Mitigation Scores
Risk ID | Program | Risk Name | Risk Description | Date Captured | Risk Owner | Pre-Mitigation Impact | Pre-Mitigation Likelihood | Pre-Mitigation Score | Current Impact | Current Likelihood | Current Score | Post-Mitigation Impact | Post-Mitigation Likelihood | Post-Mitigation Score | Risk Response | Mitigation Plan / Actions | Current Status | Risk Proximity | Workstream | Operational or Project Risk | Escalation Level | Last Review Date | Next Review Date | Target Completion Date | Historical Progress | Notes
RIPSRSK0001 | Conduct industry research on trends and emerging technologies | Inadequate Industry Intelligence Risk | Research may fail to capture current industry trends, emerging technologies, market shifts, or stakeholder expectations, leading to weak policy and regulatory decisions. | 2026-03-05 | Director RIPS | 1 | 3 | 3 | 4 | 5 | 20 | 3 | 1 | 3 | Reduce | Improve timely data collection | In progress | medium term | Operations | Project | DG | 30/6/2026 | 30/9/2026 | 30/12/2026 | Training was conducted prior to the data distribution in Q2 | Work in progress
RIPSRSK0002 | Conduct Regulatory Impact Analysis | Poor Regulatory Impact Assessment Risk | Regulatory proposals may be assessed with incomplete data, weak assumptions, or limited stakeholder input, resulting in ineffective or burdensome regulations. | 2026-03-06 | Director RIPS | 2 | 2 | 4 | 5 | 3 | 15 | 2 | 3 | 6 | Reduce | Be intentional to priortise Regulatory Impact Analysis | [7 empty] | 30/12/2027
RIPSRSK0003 | Implementation of the Authority's Strategic Plan and yearly corporate objectives | Strategic Plan Implementation Risk | Planned strategic activities and annual corporate objectives may not be implemented on schedule due to funding gaps, weak coordination, staff capacity limits, or changing priorities. | 2026-03-07 | Director RIPS | 3 | 2 | 6 | 3 | 4 | 12 | 2 | 1 | 2 | Reduce | 1. Improve revenue collection to help generate funds to meet the budgetary requirements for the objective. 2. Alternative sources of revenue 3. Implement procurement automation tools to ensure the timely processing of purchase orders. | [7 empty] | 30/12/2028
RIPSRSK0004 | Monitor and evaluate the performance of the Corporate Strategic Objectives | Weak Performance Monitoring Risk | Corporate objectives may not be properly tracked, measured, or reported, making it difficult to identify underperformance or take corrective action. | 2026-03-08 | Director RIPS | 4 | 5 | 20 | 2 | 5 | 10 | 2 | 4 | 8 | Reduce | 1.Escalate late submission of Divisional performance data for the Director General's intervention. 2. Automate the submission of performance data to ensure effectiveness and efficiency | [7 empty] | 30/12/2029
RIPSRSK0005 | Industry Data Collection and Management | Industry Data Quality and Management Risk | Data collected from industry players may be incomplete, inaccurate, delayed, poorly stored, or inconsistently reported, affecting analysis and decision-making. | 2026-03-09 | Director, RIPS | 4 | 3 | 12 | 2 | 5 | 10 | 3 | 3 | 9 | Reduce | 1. Adherance to timelines by the Service Providers in submitting data. Tripartite adhering to laid down procedures and timelines in executing its mandate. 2. Service Providers should receive the penalties associated with non-submission of Data. 3. Data collections should include all Licensed service provider under the Authority. | [7 empty] | 30/12/2030
RIPSRSK0006 | Implement guidelines for the computation of 1% Regulatory Fees | Regulatory Fee Computation Compliance Risk | Guidelines for computing 1% regulatory fees may be misapplied, misunderstood, disputed by industry players, or inconsistently enforced. | 2026-03-10 | Director Legal, Director RIPS | 1 | 5 | 5 | 5 | 3 | 15 | 4 | 1 | 4 | Reduce | 1. Organise Quarterly workshops to resensitize Operators on compliance and evaluate new challenges. 2. Prefer penalties for non-compliance of guideline application. 3. Collect Feedback for continous improvement 4. Annually review the guidelines on lessons learnt. | [7 empty] | 30/12/2031
RIPSRSK0007 | Determine and implement Wholesale Interconnect Rate for 2024–2026 | Wholesale Interconnect Rate Determination Risk | Wholesale Interconnect Rate decisions may be delayed, challenged, based on insufficient data, or resisted by operators, affecting regulatory credibility and market stability. | 2026-03-11 | DG, Director RIPS, Director RA | 5 | 5 | 25 | 4 | 4 | 16 | 2 | 3 | 6 | Reduce | 1. Organise Workshops for continous sensitization. 2. Perfer percuniary penalties for non-compliance. 3. Great channels for escalation on dispute resolution on the application of the WIR. | [7 empty] | 30/12/2032
[8 empty] | 0 |  |  | 0 |  |  | 0

## Lookups
Risk Impact |  |  | Risk Likelihood |  |  |  | Risk Response
1 | Very Minor |  | 1 | 1 - 20% |  |  | Avoid
2 | Minor |  | 2 | 21 - 40% |  |  | Reduce
3 | Moderate |  | 3 | 41 - 60% |  |  | Fallback
4 | Significant |  | 4 | 61 - 80% |  |  | Transfer
5 | Catastrophic |  | 5 | 81 - 99% |  |  | Share
Accept
| Impact | 5 | 10 | 15 | 20 | 25
|  | 4 | 8 | 12 | 16 | 20
|  | 3 | 6 | 9 | 12 | 15
|  | 2 | 4 | 6 | 8 | 10
|  | 1 | 2 | 3 | 4 | 5
Likelihood